## Slide 1: HIE-ISOLDE Status Report
Yacine Kadi on behalf of HIE-ISOLDE project team
ISOLDE Collaboration Committee Meeting, 3 November 2011
Notes: Following the departure of Matteo Pasini, I have been mandated to take over the technical coordination of the project in addition to project leader

## Slide 2: Outline
Project Organization
Main Highlights & R&D Activities
Project Schedule
Budget Review + Resources
Int. Collaboration
Outlook

## Slide 3: Project Organization
New Mandate of the Technical Coordinator is under approval
SRF activities within HIE-ISOLDE (BE/RF)
      New mandate of Physicist in charge
      Definitions and agreement on WUs (responsibilities and deliverables)
      Chopper/kicker line Design:
        Carry out the study of the chopper/kicker with the associated optics for the new RIB transfer line.
        Provide functional specifications, check and validation of a multi-harmonics RF structure upstream the RFQ.
Beam Dynamics Activities (TE/ABT)
      Act as interface with the Physics working group.
      Carry out Beam Dynamics study with realistic field and error study for the new RIB transfer line.
      Provide functional specifications, check and validation of the beam dynamics

## Slide 4: Outline
Project Organization
Main Highlights & R&D Activities
Project Schedule
Budget Review + Resources
Int. Collaboration
Outlook

## Slide 5: Highlights (1/2)
Dismantling and relocation of “hangar à camion” over => start of civil engineering work at ISOLDE
Invitation for Tenders are being launched
      Cryogenic Plant
      HVAC System
Market surveys are being launched
      Cooling System
      Cryomodule vessel and support
      SC solenoids
      Clean room at SM18

## Slide 6: Highlights (2/2)
SC cavity activities review by international expert panel => Final recommendations and actions taken
Increase sputtered film RRR to at least 20
      => Implementation of High temperature sputtering
Increase the number of substrates available
      => 2 additional prototype cavities are under fabrication
Increase the testing throughput in SM18
      => 2 new inserts and additional thermal screen are being manufactured => in principle even envisage 2nd test cryostat
      => The turn around can be potentially improved from 6 weeks to 3 weeks

## Slide 7: R&D Activities
Pre-series High-Beta Cavity
High-Beta Cryomodule Design
RF Measurements
Sputtering Developments
Detailed presentations at 7th HIE-ISOLDE Steering Committee meeting:
https://indico.cern.ch/conferenceDisplay.py?confId=159608

## Slide 8: Superconducting RF cavity (by O. Capatina EN/MME)
Design high- beta cavities – NEW VERSION
  Material: Cu-OFE 3D forged
  Manufacturing technique for serial production: 3D machning, EB welding
    Reduces considerably the number of critical welds
    No annealing
    Repetitive precision of beam ports
  By design
    Reduce sensibility to pressure fluctuation
    Increase final precision with no need of plastic deformation
    The same external envelope as the old design

## Slide 9: Superconducting RF cavity (by O. Capatina EN/MME)
Manufacturing high- beta cavities – NEW VERSION
  One prototype of the “new version” manufacturing ongoing
    Concept validation by calculations and tests

## Slide 10: R&D Activities
Pre-series High-Beta Cavity
High-Beta Cryomodule Design
RF Measurements
Sputtering Developments
Detailed presentations at 7th HIE-ISOLDE Steering Committee meeting:
https://indico.cern.ch/conferenceDisplay.py?confId=159608

## Slide 11
The HIE-ISOLDE cryomodule: the vacuum vessel (2/3)
Shape simplified thanks to optimisation of the inner components

## Slide 12
The HIE-ISOLDE cryomodule: Top plate
All services arrive through the top plate.

## Slide 13
The HIE-ISOLDE cryomodule: Interconnection module
Class 100
ISO 5

## Slide 14
The HIE-ISOLDE cryomodule: Warm steerer
On the left: magnetic 3D model in OPERA software environment. On the right: mechanical 3D model in the CATIA software
Ref: Compact Inter-cryomodule Combined Corrector Magnets for the HIE-ISOLDE Project at CERN, MT22, J Bauche
Parameter | Units | H-I corrector magnets
Overall width x height | (mm) x (mm) | 490 x 460
Overall length | (mm) | 70
Iron length | (mm) | 28
Free aperture | (mm) x (mm) | 130 x 130
Peak current | (A) | 40
Current density | (A/mm2) | 2.1
Dissipated power (per plane) | (W) | 76
Coils resistance @ 20°C (per plane) | (mΩ) | 47
Magnetic inductance (per plane) | (mH) | 8.8
Peak flux density (per plane) | (mT) | 20
Integrated flux density (per plane) | (mT·m) | 6.1
Max. flux density in iron (both planes powered) | (T) | 1.52
Max. relative integrated field error in GFR (r = 15 mm) |  | < 7.6E-4
Max. stray field in a transversal plane @ z = 100 mm from magnet center (both planes powered) | (mT) | 11
Design Parameters of HIE-ISOLDE Corrector Magnet
TE-MSC: J Bauche
Prototype under manufacturing
Magnetic measurement before end of 2011

## Slide 15
The HIE-ISOLDE cryomodule:Diagnostic box (E Bravin / BE-BI&J Galipienzo: AVS)
BE-BI: E Bravin (in collaboration with AVS)
Design to be completed by end 2011

## Slide 16
The HIE-ISOLDE cryomodule: Cleanroom (O Brunner BE/RF)
Specification available
Cryomodule assembly procedure definition started
Class 10000
ISO 7
5.3 m
4.5 m
Class 100
ISO 5
≈ 5 m
≈ 5 m
≈ 5 m
Ready for use in September 2012

## Slide 17
Planning: Details of cryomodule 1 (proto)
Vacuum vessel (long lead item) including top plate
Nov 2011: Design completed
Dec 2011: IT sent out / 1unit + 1 in option
March 2012: Cryomodule detailed design review
Nov 2012: Start of assembly in cleanroom / All components available
Sep 2013: Cryomodule 1 assembled
May 2014: CM available for installation including 3 months allocated for corrective actions
`
! Cryo shutdown in SM18 not taken into account !
Back-up: thermal test with thermal models
CM 1 will be a proto-flight model,
Assembled at CERN
By CERN staff

## Slide 18: R&D Activities
Pre-series High-Beta Cavity
High-Beta Cryomodule Design
RF Measurements
Sputtering Developments
Detailed presentations at 7th HIE-ISOLDE Steering Committee meeting:
https://indico.cern.ch/conferenceDisplay.py?confId=159608

## Slide 19
“A long and winding circle…” (O. Brunner BE/RF)
Jan11
Feb11
Mars11
Apr11
May11
June11
July11
Aug11
Sept11
Oct11
Nov11
Dec11
Dec10
Nov10
Oct10
Pb with cryo and RF cable
RF Test Q1
RF Test Q1
RF Test Q2
RF Test Q1
RF Test Q2
Leak in insert
Cryo shutdown
RF Test Q2
Burned RF connector, RF coupler pb
Leak in coating system
Chemistry
Coating
Rinsing & Clean Room Assembly
Cool Down
Clean Room Assembly
Insertion in cryostat
RF Conditioning, RF Measurements
Warm Up, Venting
Clean Room Assembly
Testing throughput: 3-4 weeks
RF coupler blocked

## Slide 20
Cavity design: power coupler (O. Brunner BE/RF)
  Several problems during cavity tests
    problems during cavity tests (blocked)
  Design review has started (E. Montesinos, BE/RF)
    prototype: May’12
  Motorization and position control ready but not validated yet

## Slide 21
  Cryostat and vertical RF test stand
    Cavity insert
    Actively cooled thermal screen
  Operational experiences
    Improvement of the RF cable thermalization
      Warm side: burned RF connector (and leak) due to condensation
      Cold side: avoid warming up the cavity
    Large efforts from the cryo team to establish cool down procedure and maintain LHe pressure stability:
      Actual LHe transfer line -> leads to He pressure instabilities (will be replaced next year)
      Try to keep cavity warmer that cold screen
    Cavity heating system must be improved
    Problem of the year: Leak in the insert assembly:
      Developed a He leak (at cold) after several cool downs/warm ups (April)
      Leak was finally “located” (TE-VSC) and repaired (EN-MME) mi-June
Clean room assembly & RF testing (2)

## Slide 22
RF Test Results (O. Brunner BE/RF)
Chart: Eacc (MV/m)
| 0.213874552 | 1.098396428155672 | 1.2022896596710579 | 1.3485253409713269 | 1.5212798467455311 | 1.6796125536796429 | 1.804509247281314 | 1.9431624610198821 | 2.0460164068335058 | 0.87601009706565702 | 0.95490267943128404 | 0.72220270703434797 | 0.63483244119941096 | 0.40941062754900398 | 0.53230324286273301 | 0.21387455156733801 | 1.802017946951102
Q1 Mag Dec 10 - 1st | 2630000000 | 259591604.885 | 205252658.2563 | 139490117.1649 | 80155137.1266 | 46485242.4651 | 31768541.5676 | 19545545.1097 | 13569979.4732 | 391076036.6479 | 345754835.1637 | 502304398.1943 | 566253655.071 | 738583479.2099 | 724899097.2865 | 2626373262.6222 | 31817875.7603
Q1 Mag Dec 10 - 2nd | 81018557.2728 | 19490041.9495 | 17437315.4371 | 12737991.6469 | 10870290.1963 | 7863916.2989 | 4527594.0396 | 3941663.6378 | 25085572.9788 | 28817622.5282 | 50481127.8822 | 57827214.8045 | 67716951.3827 | 81018557.2728 | 97143333.2939 | 3721683.8988 | 3174658.1289 | 24443112.3493 | 36888822.6534 | 29759246.5326 | 88324165.9238 | 46674596.99 | 34142976.8852 | 8028814.4484 | 33335407.7267 | 64471629.9318
Q2 Mag Apr 11 | 73337016.0793
Q1 Diode Jul 11 | 2640504.6701 | 2317878.3942 | 2119900.5602 | 1934521.349 | 1810574.4511 | 1919806.1858 | 1897720.1615 | 1906480.4146 | 2292734.7137 | 2253720.3612 | 2097263.963
Q2 Mag Sept 11 | 669000000 | 533265513.8358 | 510830862.559 | 489245705.0203 | 467031460.7694 | 447781157.8981 | 421910313.1017 | 366119583.5909 | 288206256.6435 | 199869457.9659 | 86929914.9023 | 17411625.9566 | 7844010.2698 | 6620642.8585

## Slide 23
Cavity Tests
RF Testing Operational
Clean room & RF Test Protocol Established
Coating tests in progress (VSC)
Fall 2012:
5 RF couplers & tuners validated & built
New clean room built
Coating recipe validated (TE/VSC)
5 cavities built (substrate) (EN/MME)
May 2013:
5 fully equipped cavities tested & validated
CM test place operational (controls, LLRF, RF power)
All CM parts procured (TE/MSC)
September 2013:
CM in SM18 bunker
CM fully assembled (TE/MSC)
December 2013:
Cryomodule tested & validated (vacuum, cryo, RF)
A goal is a dream with milestones
(O. Brunner BE/RF)
Notes: SmartArt custom animation effects: upward arrow process
(Basic)
To reproduce the SmartArt effects on this slide, do the following:
On the Home tab, in the Slides group, click Layout, and then click Blank.
On the Insert tab, in the Illustrations group, click SmartArt. In the Choose a SmartArt Graphic dialog box, in the left pane, click Process. In the Process pane, click Upward Arrow (sixth row, third option from the left), and then click OK to insert the graphic into the slide.
Select the graphic, and then click one of the arrows on the left border. In the Type your text here dialog box, enter text. (Note: To create a bulleted list below each heading, select the heading text box in the Type your text here dialog box, and then under SmartArt Tools, on the Design tab, in the Create Graphic group, click Add Bullet. Enter text into the new bullet text box.)
On the slide, select the graphic. Under SmartArt Tools, on the Design tab, in the SmartArt Styles group, do the following:
  Click Change Colors, and then under Colorful click Colorful Range - Accent Colors 3 to 4 (third option from the left).
  Click More, and then under Best Match for Document click Intense Effect (fifth option from the left).
On the Home tab, in the Font group, select Calibri from the Font list, and then select 24 from the Font Size list.
Select the text in the first text box from the left. Under SmartArt Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Olive Green, Accent 3, Darker 25% (fifth row, seventh option from the left).
Select the text in the second text box from the left. Under SmartArt Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Aqua, Accent 5, Darker 25% (fifth row, ninth option from the left).
Select the text in the third text box from the left. Under SmartArt Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Purple, Accent 4, Darker 25% (fifth row, eighth option from the left).
To reproduce the animation effects on this slide, do the following:
On the Animations tab, in the Animations group, click Custom Animation.
On the slide, select the graphic. In the Custom Animation task pane, do the following:
  Click Add Effect, point to Entrance, and then click More Effects. In the Add Entrance Effect dialog box, under Basic, click Wipe.
  Under Modify: Wipe, in the Direction list, select From Left.
  Under Modify: Wipe, in the Speed list, select Fast.
  Also in the Custom Animation task pane, select the wipe effect. Click the arrow to the right of the wipe effect, and then click Effect Options. In the Wipe dialog box, on the SmartArt Animation tab, in the Group graphic list, select One by one.
Also in the Custom Animation task pane, click the double arrow under the wipe effect to expand the contents of the list of effects.
Also in the Custom Animation task pane, select the second wipe effect and then do the following:
  Click Change, point to Entrance, and then click More Effects. In the Change Entrance Effect dialog box, under Exciting, click Curve Up.
  Under Modify: Curve Up, in the Start list, select With Previous.
  Under Modify: Curve Up, in the Speed list, select Very Fast.
Also in the Custom Animation task pane, select the third wipe effect and then do the following:
  Click Change, point to Entrance, and then click More Effects. In the Change Entrance Effect dialog box, under Moderate, click Descend.
  Under Modify: Descend, in the Start list, select With Previous.
  Under Modify: Descend, in the Speed list, select Very Fast.
  Click the arrow to the right of the third wipe effect, and then click Timing. In the Descend dialog box, on the Timing tab, in the Delay box, enter 0.5.
Also in the Custom Animation task pane, select the fourth wipe effect and then do the following:
  Click Change, point to Entrance, and then click More Effects. In the Change Entrance Effect dialog box, under Exciting, click Curve Up.
  Under Modify: Curve Up, in the Start list, select On Click.
  Under Modify: Curve Up, in the Speed list, select Very Fast.
Also in the Custom Animation task pane, select the fifth wipe effect and then do the following:
  Click Change, point to Entrance, and then click More Effects. In the Change Entrance Effect dialog box, under Moderate, click Descend.
  Under Modify: Descend, in the Start list, select After Previous.
  Under Modify: Descend, in the Speed list, select Very Fast.
Also in the Custom Animation task pane, select the sixth wipe effect and then do the following:
  Click Change, point to Entrance, and then click More Effects. In the Change Entrance Effect dialog box, under Exciting, click Curve Up.
  Under Modify: Curve Up, in the Start list, select On Click.
  Under Modify: Curve Up, in the Speed list, select Very Fast.
Also in the Custom Animation task pane, select the seventh wipe effect and then do the following:
  Click Change, point to Entrance, and then click More Effects. In the Change Entrance Effect dialog box, under Moderate, click Descend.
  Under Modify: Descend, in the Start list, select After Previous.
  Under Modify: Descend, in the Speed list, select Very Fast.
To reproduce the background effects on this slide, do the following:
Right-click the slide background area, and then click Format Background. In the Format Background dialog box, click Fill in the left pane, select Gradient fill in the Fill pane, and then do the following:
  In the Type list, select Linear.
  In the Direction list, click Linear Right (first row, fourth option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 39%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click Olive Green, Accent 3, Lighter 60% (third row, seventh option from the left).
To increase the size of the SmartArt graphic so that it spans the entire slide, do the following:
On the slide, select the graphic.
Point to the top right corner of the graphic border, until a two-headed arrow appears. Drag the top right corner of the graphic border into the top right corner of the slide.
Point to the bottom left corner of the graphic border, until a two-headed arrow appears. Drag the bottom left corner of the graphic border into the bottom left corner of the slide.

## Slide 24: R&D Activities
Pre-series High-Beta Cavity
High-Beta Cryomodule Design
RF Measurements
Sputtering Developments
Detailed presentations at 7th HIE-ISOLDE Steering Committee meeting:
https://indico.cern.ch/conferenceDisplay.py?confId=159608

## Slide 25: Coatings without cooling
Magnetron coating
...”increase sputtering temperature”:
270 °C (1kW) and 330 °C (2 kW)
RRR for 150 °C coatings
Now:
Double number of quartz samples (RRR measurement)
Full length of cavity surface lined with copper strips for SEM analysis

## Slide 26: Coatings without cooling
...”increase sputtering temperature”:
260 °C (1kW) and 340 °C (2 kW)
Bias diode coating
RRR for 150 °C coatings

## Slide 27: Further testing performed
....“Increase sputtering rate”
Coating of a copper cavity with liquid cooling (Q2.4) to identify the maximum coating power attainable while keeping the cavity’s outer wall at 150 °C  2.5 kW
Coating at same power of 2.5 kW on s.steel dummy  330 °C
This test confirms the necessity of a copper dummy cavity for sample testing, in order to reproduce the same temperature profile

## Slide 28: Cavity coatings
 | Q2.3 | Q1.5 | Q2.5 | Q1.7
Type | Magnetron | Diode | Magnetron | Magnetron
Coated | March | April | September | (this week)
Nominal pressure | 8x10-3 mbar | 1.5x10-1 mbar | 8x10-3 mbar | 8x10-3 mbar
Nominal power | 1 kW | 1 kW | 1 kW | 2 kW
Coating time | 8 h | 38 h | 8h | 3.5 h
RF test | Only one RF point measured | Yes | Yes | Next
Comments |  | No coating on beam line of inner conductor | Repetition of Q2.5 No sputter etching | No cooling (test: 410 °C) NEG assisted pumping

## Slide 29: Future plans
Validate high-temperature coatings by magnetron sputtering by end 2011
Goals set by the project:
  on-specs by March 2012
  Production coatings start 1Q2013

## Slide 30
Cold Box  500 liters of LHe
Dewar  2000 liters of volume ≈ 1000 liters of LHe
Picture S.Maridor
6 cryo-modules inside tunnel  6 x 150 liters of LHe
Tunnel dim. = 22.6 m x 3.2 m x 4m  Tunnel volume = 290 m3
General Safety (A.-P. Bernardes)
Oxygen deficiency
In collaboration with N.Delruelle (TE/CRG)

## Slide 31
Noise propagation impact on nearest buildings
Noise impact outside of CERN
Impact outside of CERN too high – Need to invest on “Low noise equipment” - Collaboration with EN/CV on going
General Safety (A.-P. Bernardes)

## Slide 32
Radioprotection (A.-P. Bernardes)
Radiation shielding
First estimation of shielding reinforcement civil engineering of the primary area tunnel will not support so much weight
Pictures from V.Barozier
In collaboration with A.Dorsival, J.Vollaire DGS/RP and V.Vlachoudis EN/STI

## Slide 33
GPS
HRS
HRS separator
GPS separator
Protons
- Impact on actual existing shieldings ??
Radioprotection (A.-P. Bernardes)
TO BE DONE
- Respect of actual radioprotection limit values ??
Limit for public:
1 mSv/year
Experimental hall – Supervised area:
6 mSv/year
Limit for public:
1 mSv/year
Experimental hall – Supervised area:
6 mSv/year
Controlled Area?
ESR10 Marie-Curie fellow not started
No more support from Y.Romanets
In collaboration with A.Dorsival, J.Vollaire DGS/RP and V.Vlachoudis EN/STI

## Slide 34
REX post-accelerator shielding for RF emitting X-ray.
TO BE DONE:
Radioprotection
In collaboration with A.Dorsival and J.Vollaire DGS/RP

## Slide 35
Evaluation and shielding of secondary radiation fields from heavy ions
Shielding – Access control – limitation of beam intensity?
TO BE DONE
3MeV/nucleon  10 MeV/nucleon
Radioprotection
In collaboration with A.Dorsival and J.Vollaire DGS/RP

## Slide 36: Design Study Status
Richard Catherall EN-STI-RBS
HIE-ISOLDE Steering Committee
31st October, 2011

## Slide 37: Intensity Upgrade: Overview
Target & FE Design
WP 5
Targets
WP5.1
Front End
WP 5.2
Mechanical
WP5.2.3
Thermo mechanical
WP 5.1.2
Materials
WP5.1.1
Optics
WP 5.2.2
Fluka
WP5.1.1
HV systems
WP5.2.1
Mechanical
WP 5.1.2
Cooling & Ventilation
WP 6.2
Vacuum
WP 6.5

## Slide 38: Beam Quality: Overview
Separator areas
WP 7.3
Pre-mass separator
WP 7.3.3
RFQ Cooler
WP 7.3.2
Magnet
WP 7.3.1
Matching
Integration
Test stand
Wein filter
RFQ Filter
Source to RFQ
RFQ to final focus
HT platform
Redesign
Field design
Magnet design
NMR regulation
Ion ray tracing
High order correction
BI & slits
Technical specifications
Off-line separator
WP 7.2
REXEBIS upgrade
WP 7.5
Low level controls
WP 6.8

## Slide 39: What’s next …..
Kick-Start of the Design Study for the Intensity Upgrade
Validation of the Beam Transfer Line Optics (TE/ABT)
      Magnet design
      Estimation of power converters
      Beam diagnostics
      CV, Vacuum, etc…
Chopper Line Design => ECR in preparation
IAP => 9-10 January 2012
Cryomodule Design Review => March/April 2012

## Slide 40: Outline
Project Organization
Main Highlights & R&D Activities
Project Schedule
Budget Review + Resources
Int. Collaboration
Outlook

## Slide 41: HIE-ISOLDE Planning
Hie-Isolde installation planning in EDMS:
Projects – Accelerators - Hie-Isolde – Infrastructure & Integration - Planning
https://edms.cern.ch/nav/P:CERN-0000072786:V0/P:CERN-0000090679:V0/TAB3

## Slide 42
Courtesy: Matteo Pasini, Matthew Fraser
Modular installation
Schematic:

## Slide 43
High-β Cryo Modules 3 & 4: Jan - Feb 2016
Chopper Line
4330
22600
Modular installation
High-β Cryo Modules 1 & 2: Aug 2014 – Oct 2014
REX physics at 5.5MeV/u for 2015
First beam at 5.5MeV/u autumn 2014
Energy 10MeV/u
Low-β Cryo Modules 5 & 6: 2017 ?
and Chopper ?

## Slide 44
Hie-Isolde SC Linac
First 10MeV/u by March 2016
Hie-Isolde SC Linac:
Bunched beam by 2017 ?
5.5MeV/u by the autumn of 2014

## Slide 45
Beam Transfer Line
The bend
Stage 2:
Miniball
Miniball
Actar / Helios
TSR
Spectrometer
Exp. station
2nd Miniball move and Spectrometer installation
TSR and beyond..
Stage 3:

## Slide 46: Progress Monitoring

## Slide 47: Progress Monitoring

## Slide 48
Cost studies new B 507
Study on the use of modular cabins instead of a full concrete building
Phase 1: estimate 120kChf
- dismounting the present building - construction permit - adapting the concrete foundation
Phase 2: estimate 520kChf
- installation of modular cabins, interconnected and on 2 floors - total surface 460 m2
- not taken in account electrical installations, CV, Labo’s, etc.
  Advantages: - lower costs
  - fast construction
  - flexible work floor
  Cost study:
  Eliseo Perez-Duenas GS/SE

## Slide 49: Outline
Project Organization
Main Highlights & R&D Activities
Project Schedule
Budget Review + Resources
Int. Collaboration
Outlook

## Slide 50: Budget Review
As defined in MTP 2010
(175 FTE)
Total budget of 35.8 MCHF (2010 – 2015) with two funding sources:
  External funding (incl. Isolde Coll.)
    LINAC (17.5 MCHF)
      5.5 AMeV + beam line stage1 ~ 8.5 MCHF (6.3 MCHF secured)
  CERN
    Management (0.2 MCHF)
    Infrastructure (15.2 MCHF) => +15% (consolidation of testing infrastructure )
    Design studies for intensity upgrade (2.0 MCHF)
    Safety (0.9 MCHF) => +25%

## Slide 51: Total Projected Expenditures
Chart: 
| 2010 | 2011 | 2012 | 2013 | 2014 | 2015
Baseline | 731 | 5643 | 15902 | 25429 | 33007 | 35415
Current | 437 | 2157 | 10806 | 22075 | 31044 | 35673

## Slide 52: SC Linac Expenditures
Chart: 
| 2010 | 2011 | 2012 | 2013 | 2014 | 2015
SC Linac Baseline | 401 | 3095 | 6894 | 11373 | 15341 | 17724
SC Linac Current | 330 | 972 | 4257 | 8874 | 13021 | 17515
Income Secured
Income Secured + Applied
10 MeV/u + TL1 and TL2
5.5 MeV/u + TL1 and TL2

## Slide 53: Expenditures SC Linac (1/3)

## Slide 54: Expenditures Infrastructure (2/3)

## Slide 55: Expenditures DS + Safety (3/3)

## Slide 56: Human Resources (1/2)
CERN Staff
  Resources defined by group leaders (95 FTE over 5 years) => included in APT
Fellows (70 FTE)
  5 FTE paid on departmental budget
  9 FTE paid by Isolde Collaboration
  56 FTE paid by ITN3 Marie Curie Contract (20 fellows)

## Slide 57: Human Resources (2/2)
  => Funding request for BE/RF fellow (starting 2012) to upgrade the present scenario of the HIE-ISOLDE linac with the possibility to have 100 ns clean bunch spacing.
  => Funding request for TE/ABT fellow for beam dynamics 50% for 2012/2013
  => Funding request for EN/MME fellow for mechanical design and spec preparations 100% for 2012/2013

## Slide 58: 5 CATHI Positions still open (selection ongoing)
ESR10: Target conceptual design#2
ER1: LLRF Control
ER2: Beam Instrumentation
ER3: Design study of a replacement charge breeder for REXEBIS
ER4: Radiation Protection Studies
15 CATHI positions already filled

## Slide 59: Status of HIE-ISOLDE Collaborations
IPN-Orsay
    Discussions concerning special contribution (LLRF, cavity ancillaries, …)
    Availability of test cryostat for HIE-ISOLDE cavity RF tests
    MoU in preparation
Korean MEST to allocate 200 kUSD/year for joining ISOLDE Collaboration => under approval
BARC (India)
    Discussion concerning in kind contribution (production of copper cavity substrates and cryostats)
    Discussion with DAE (funding agency) for joining ISOLDE Collaboration
Application to Wallenberg Foundation on priority list

## Slide 60: Outlook
SC Cavity prototype cold tests @ SM18
Cryomodule Design
Procurement of Cooling & Ventilation Plant
Procurement of the Cryogenics Plant
Start of the civil engineering works
Kick-start of Design Study for intensity upgrade

## Slide 61
Thank you very much for your attention
HIE-ISOLDE web site -> http://hie-isolde.web.cern.ch/hie-isolde/
CATHI-ITN web site -> https://espace.cern.ch/Marie-Curie-CATHI/default.aspx